## Broken Functionality
Broken Functionality
Sl.No | Issue | Rootcause | Solution | Impacted files
1 | User Last names not displayed in users page | Code for displaying last names not present | Included code for displaying lastname | user.html
2 | Filter for first name and last name broken | Code for filtering by first name was trying to match with last name. Code for filtering by last name was not present | Code corrected | users.component.ts
3 | Edit button opens a dialog but no user input fields are being displayed | User object is not sent as input to editUser function and UserEditComponent object not set | Code corrected | users.html, users.component.ts
4 | Home page not found | Route link was mispelled | Code corrected | app.component.ts

## New Functionality
New Functionality
Sl.No | Change | Approach | Impacted files
1 | Display circular avatars of users before every user name | Image tag was added to code to display images from user object. A class was created for circular display in scss file | user.html, user.scss
2 | Display current age of users in () next to every user name | Function to calculate age of users was included and called in html page | user.html, user.component.ts
3 | Update User - Persist the updated values | Update event included in Update button in html page. Update function written to persist data. After persistance, code was included to close the pop up and refresh the user list. | user-edit.html, user-edit.component.ts, users.component.ts
4 | Sort users | TBD | TBD
5 | Implement pagination for user list | Installed dependency for pagination using 'npm install ngx-pagination' and declared the same in package.json and app.module.ts. Implemented code in html for paginating the list. | users.html, package.json, app.module.ts
6 | Delete User | Added a delete button in user.html with event emitter. Declared onDelete emitter in UserComponent. Added onDelete function in user-info tag in users.html. Implemented delete user function in UsersComponent with a confirm message. | user.html user.component.ts users.html users.component.html
7 | Include new About page | New AboutComponent written with desired html content. New link for About menu added in AppModule and route path added in AppComponent file. Path and Component mapped in AppRoutes file. | about.component.ts app.module.ts app.routes.ts app.component.ts